## Sheet1
Log for CA website - Student No:10352606
Date | Time (hours)
2017-03-30 | 2 | Separated CA brief into content for individual. Contact form. Preliminary design.
2017-04-01 | 3 | Created 6 empty pages Navigation links & hyper-text links CSS file – called by all pages. Accessibility idea – hyper-text links in footer. Sourced graphic of B&B rooms – inserted onto site.
2017-04-02 | 3 | Form – styling with CSS.
2017-04-04 | 1.5
2017-04-14 | 1.5 | Styling on headers & background image – fixed so other elements can scroll underneath. Rounded corners on headers & contact form.
2017-04-15 | 1.5 | Added ‘Trip Advisor’ logo & JavaScript file to change image with mouse over options.
2017-04-16 | 4 | Edit images sizes & resolution – using PixR application. CSS styling. Embedded Google Maps – time consuming false start after using google’s api key (not required!!!)
2017-04-19 | 2 | General CSS styling. Google maps with API vs simple embedding.
2017-04-20 | 1.5 | Menu design.
2017-04-21 | 7.5 | Graphics header / banner Changed background to tiled / repeated image instead of single large photograph image. Implemented Menus & navigation 2 column wire page structure. General styling.
2017-04-22 | 6 | Created a master template derived from home page. Applied template to all other rough draft pages – draft site is now functionally visible. More work on banner / logo. Styling images for rooms & sightseeing pages into gallery type structure
2017-04-23 | 3.5 | Fixing classes & id that were conflicting with each other throughout the site!! - For hyper link formatting: nav menu ul list VS images ul list(s).
2017-04-24 | 5 | Validating & correcting css & html code. Implemented links within ‘rooms’ page so as to be able to go to room selected. Content disappeared beneath header banner.!!!!!!
2017-04-25 | 5 | Back to top of page link – on all pages Modularise css code – using class & id’s simultaneously on the same element. Rounded corners on images.
2017-04-28 | 4 | JavaScript for forwards & backwards navigation CSS styling.
2017-04-29 | 8 | Gallery of photos using JS – optimising images entire site. Styling text to flow around images. Modularising code. Display Date function – added to left navigation column.
2017-04-30 | 9 | JavaScript validation for form JavaScript Photo Gallery & re optimising images for gallery Changed Navigation CSS Styling (x lots)
2017-05-01 | 8 | Misc: HTML / CSS / JavaScript / Styling / Testing
2017-05-02 | 3.5 | Fixed JS issue – problems with window.onload - scripts loading & not being loaded at required time. Used event listener to solve 3 ½ hours.
2017-05-03 | 2 | SEO – page titles (½ hour) Alt tags for all images on site (1 ½ hours)
2017-05-04 | 3 | Testimonials on most pages. Single on image on pages with no images Rel = no follow Updated hyperlinks !! NO JavaScript Option for people with no javascript enabled. Tidied up indentation of all html code & fixed & validated mistakes using W3C validator
2017-05-05 | 1.5 | Tidied up CSS file – proper indentation & commenting. Fixed header display resizing issue. Wrote meta descriptions for each page in the site.
2017-05-07 | 2.5 | Composed descriptions for meta-tags & inserted into html. Tidied up JavaScript code & image gallery code. Revalidated entire site. Updated dated all log entries in excel.
2017-05-08 | 7 | Reasearched and implemented ARIA's 'landmark role'. Implemented sitemap with textlinks in the footer of each page. Fixed form validation issue which was allowing the input of white - space to be considered a valid input. Changed the functionality of all images on the home page from - mouse-over to onclick. Final W3C validation. Report writing.
9-May_17 | 4 | Finished, edited & formatted report. Double checking everything. Zipped up all files & submit.